## Planilha1
Data	Hora inicio	Hora fim	Descrição	Tempo gasto
01/12/21	15:00:00	15:30:00	Visão geral e estrutura de arquivos	00:30:00		107:52:00,00
01/12/21	15:30:00	16:40:00	Tela principal frontend e importação de assets do figma	01:10:00
03/12/21	07:40:00	08:50:00	Formulário da página principal	01:10:00
03/12/21	09:40:00	12:30:00	Página da roleta	02:50:00
08/12/21	07:50:00	09:00:00	Animação de rotação e background a roleta	01:10:00
09/12/21	09:10:00	10:40:00	Finalizando estrutura da roleta	01:30:00
09/12/21	15:20:00	16:35:00	Adicionando páginas restandes do frontend	01:15:00
10/12/21	07:10:00	10:40:00	Banco de dados	03:30:00
10/12/21	15:30:00	19:30:00	Roteamento admin, Tela Login, Header	04:00:00
12/12/21	14:00:00	16:30:00	Páginas GivenPrizes, Home, e PendingPrizes, com paginação dinâmica	02:30:00
14/12/21	11:00:00	13:30:00	Página RegisteredPrizes, exceto evento de edição de prêmios	02:30:00
14/12/21	14:25:00	16:30:00	Modal página RegisteredPrizes	02:05:00
15/12/21	11:30:00	12:35:00	Formulário Modal	01:05:00
18/12/21	17:00:00	18:50:00	Tela RegisteredPrizes	01:50:00
22/12/21	03:00:00	04:20:00	Página Ads	01:20:00
25/12/21	09:05:00	10:50:00	Event listeners página Ads e primeiro form página createAd	01:45:00
25/12/21	16:45:00	17:50:00	Trying to fetch data from IBGE API	01:05:00
02/01/22	09:30:00	10:20:00	Criando estrutura da API	00:50:00
02/01/22	14:30:00	15:00:00	Alterando rotas Admin e dotenv	00:30:00
04/01/22	08:55:00	11:50:00	Input de cidades e estados createAd e imageInput	02:55:00
05/01/22	10:00:00	12:40:00	Autenticação API	02:40:00
06/01/22	10:40:00	13:10:00	Error handling and admin get methods	02:30:00
06/01/22	15:30:00	17:20:00	Remaining admin methods and multipart image upload	01:50:00
07/01/22	14:40:00	15:50:00	Image upload	01:10:00
08/01/22	11:00:00	12:10:00	Image validation and save with file extension	01:10:00
08/01/22	13:30:00	15:10:00	Image resizing	01:40:00
08/01/22	15:20:00	16:40:00	Frontend refactor and Users page	01:20:00
08/01/22	17:05:00	20:00:00	Login Cookies and Get data from API on home and pendingPrizes	02:55:00
09/01/22	08:45:00	09:40:00	Ads, givenPrizes and registeredPrizes methods and rename to availablePrizes	00:55:00
09/01/22	15:50:00	16:50:00	Format API outputs and last API calls from admin frontend	01:00:00
09/01/22	18:40:00	19:15:00	Delete Ad and remove file from assets	00:35:00
10/01/22	11:30:00	12:15:00	Edit AvailablePrize	00:45:00
10/01/22	14:00:00	15:40:00	Validação e questões sobre o projeto	01:40:00
12/01/22	14:25:00	16:11:00	API Validation	01:46:00
13/01/22	11:00:00	12:05:00	Admin validators and fix date formatting issues	01:05:00
13/01/22	12:20:00	13:40:00	CreateAd frontend	01:20:00
14/01/22	12:00:00	15:30:00	Various design fixes, popup patterns, show error messages frontend	03:30:00
15/01/22	13:00:00	14:30:00	Frontend refactor and API error messages	01:30:00
15/01/22	14:50:00	16:20:00	Many Validation fixes and final method editAd	01:30:00
15/01/22	17:00:00	17:50:00	Frontend refactor and API error messages	00:50:00
16/01/22	10:00:00	11:30:00	Main public POST method generateSession	01:30:00
16/01/22	16:20:00	17:05:00	Main public GET method getAds	00:45:00
17/01/22	15:00:00	15:40:00	Public API adjustments	00:40:00
17/01/22	17:30:00	18:50:00	Debugging queries	01:20:00
18/01/22	13:50:00	14:20:00	GeneratePrize WORKS!	00:30:00
18/01/22	15:15:00	16:00:00	Backend Cookies	00:45:00
19/01/22	15:40:00	17:00:00	Better validation middleware	01:20:00
19/01/22	21:50:00	23:15:00	Fix prizes probability	01:25:00
20/01/22	10:30:00	11:20:00	Schedule resetPrizes jobs	00:50:00
20/01/22	11:20:00	12:30:00	Login Cookies public frontend	01:10:00
20/01/22	12:40:00	13:00:00	Login Cookies public frontend	00:20:00
21/01/22	12:10:00	14:20:00	Change validation, frontendCookies, requests and refactors	02:10:00
21/01/22	15:35:00	16:26:00	Trying to find library for roulette animation	00:51:00
22/01/22	11:50:00	12:40:00	Roulette switch pages and getAds method	00:50:00
23/01/22	15:40:00	17:20:00	fix styles, job timing and setPixKey Session	01:40:00
25/01/22	14:30:00	15:30:00	Validação com cliente	01:00:00
26/01/22	12:20:00	12:50:00	Roulette tip	00:30:00
26/01/22	13:50:00	16:05:00	Roulette animation	02:15:00
26/01/22	16:10:00	16:30:00	Update Pix Key	00:20:00
28/01/22	12:40:00	14:20:00	Various fixes and looking for an geotranslator API	01:40:00
28/01/22	14:20:00	15:50:00	Add sounds and optimize assets	01:30:00
01/02/22	18:50:00	19:40:00	Fix ads not showing and msg errors	00:50:00
02/02/22	13:30:00	16:30:00	Google API integration and minor fixes	03:00:00
03/02/22	19:10:00	19:35:00	Production frontend build	00:25:00
04/02/22	13:45:00	17:30:00	Create production database and deploy API, domain names	03:45:00
07/02/22	16:00:00	16:30:00	Trying to fix react-router on production	00:30:00
08/02/22	00:30:00	02:00:00	Fixing react-router on production	01:30:00
08/02/22	15:00:00	18:30:00	Minor fixes for production API and Frontend. DONE!	03:30:00
20/02/22	15:00:00	15:40:00	Create table and methods for updating the probability	00:40:00
20/02/22	19:00:00	20:10:00	Re-calculate probability equation isolating desired probability	01:10:00
22/02/22	09:30:00	11:30:00	Frontend admin page, remove text from public pages and publish	02:00:00